Closing Variance AI Agent

Scope, Approach & Dependencies — Response to the Functional Brief

Prepared for: Aurilo Group — Finance / Business Performance Team
Prepared by: ITP Team
Date: 9 July 2026    |    Version: 1.2 (materiality re-sourced to the brief; Actuals+FC confirmed, Previous Forecast ~80%)

1. Executive Summary

We have reviewed the Closing Variance AI Agent brief (Draft 1.0). The brief describes a comprehensive solution spanning variance detection, stakeholder follow-up via Microsoft Teams, a structured knowledge base, a Business Controller validation gate, and governance controls.

Our assessment is that the full brief cannot realistically be delivered within a three-week window. It effectively describes two products combined: (A) automated variance detection and draft commentary, and (B) an orchestrated collection-and-knowledge-base workflow with governance. A large part of (B) depends on inputs and infrastructure that sit outside our control.

Our proposed approach: deliver the client-defined Minimum Viable Pilot (brief, Section 15) for a single business unit — ITDS — within three weeks, and treat the remaining brief requirements as a subsequent phase.

2. Proposed Scope — ITDS Pilot (3 Weeks)

We will focus exclusively on the ITDS business unit and target the six requirements of the Minimum Viable Pilot defined in Section 15 of the brief:

| # | MVP requirement (brief §15) | Status / notes |
| --- | --- | --- |
| 1 | One business unit | ITDS only (masterDataSheet). Translated source file already prepared. |
| 2 | P&L actual vs forecast data only | ACTUAL and PREVIOUS FORECAST blocks already present in the file. |
| 3 | A small agreed set of materiality thresholds | Client to confirm final values (see Section 5). |
| 4 | Teams for questions and reminders | Requires Teams bot access (dependency — Section 4). |
| 5 | SharePoint List or Dataverse as first knowledge base | Requires owner mapping + KB store (dependency — Section 4). |
| 6 | Finance review before comments are used | Agent produces draft only; no auto-publish. |

Explicitly OUT of scope for this pilot (deferred to a later phase):

Other business units: Managed Services (MS) and Group / Management report files.

Additional dimensions: customer, cost-centre, service-area and project-level breakdowns.

Advanced routing: Business Controller validation gate and confidence-based routing (brief §7–8).

Governance: role-based access, full audit trail, version history, escalation paths (brief §14).

3. Work We Can Start Immediately (No External Dependency)

The following can proceed in parallel while the client provisions the dependencies in Section 4:

Ingestion:  parse the ITDS masterDataSheet into a normalised, auditable dataset (Current Forecast / Actuals+FC vs Previous Forecast).

Validation:  stop the pipeline if required forecast/actual columns are missing.

Variance engine:  flag every P&L line whose month-on-month forecast movement breaches any of the brief's Section 9 materiality rules (absolute > EUR25k or percentage > 10%, plus the per-line rules), and surface a highlighted top 5-10 by absolute magnitude.

LLM layer:  a provider-agnostic integration so Aurilo’s internal LLM can be connected by configuration once available; tested meanwhile with dummy figures only.

4. Dependencies Required from Aurilo

The items below are outside our control and directly determine whether the three-week pilot is achievable. We ask that all of them be initiated in Week 1 so that provisioning lead times run in parallel with our development.

4.1 Blocking dependencies (pilot cannot complete without these)

| Dependency | Needed for | What we need from you |
| --- | --- | --- |
| Internal LLM access | Generating draft commentary (core of the pilot) | Endpoint + credentials; which model; API type (Azure OpenAI / OpenAI-compatible / internal proxy); rate & quota limits; data-handling policy. |
| Microsoft Teams bot | MVP §15.4 — sending questions & reminders | Bot / app registration and permissions to send and receive messages. |
| Owner mapping + KB store | MVP §15.5 — who to ask, and where to store answers | A mapping of P&L responsibility to named people (with Teams/email IDs), and a provisioned SharePoint List or Dataverse table with write access. |

4.2 Business decisions required from the client

Materiality threshold - CONFIRMED by the brief (Section 9):  the pilot uses the brief's Example Variance Detection Rules - absolute P&L variance > EUR25k and variance percentage > 10%, plus the per-line rules (gross margin > EUR10k, expense > EUR10k, EBITA > EUR20k). Customer-revenue (> EUR15k) and recurring-variance rules are dimensional / history-based and move to Phase 2. This supersedes the 2% figure noted in the 7 Jul meeting.

Baseline - CONFIRMED (Actuals+FC):  the primary comparison is Current Forecast (Actuals+FC) vs Previous Forecast, i.e. how management expectations shifted over the past month. The Actuals+FC column meaning is confirmed.

Previous Forecast column - ASSUMPTION (~80% confidence), please verify:  we understand Previous Forecast as the same actuals for closed months but carrying last month's forecast for the future months. We are ~80% sure of this and are building the pilot on it, but ask Aurilo to confirm the Previous Forecast column before it is locked. (Actuals+FC is already confirmed - see above.)

Finance reviewer:  who reviews and approves the draft comments before reporting use.

Data refresh:  who exports the ITDS file each month, when, and to which location.

4.3 Supporting data (for later phases / robustness)

continuous, closed monthly actuals for prior periods (for recurring-variance detection).

a documented list of known timing / accounting issues to exclude.

monthly (not only quarterly) customer / service revenue if dimensional analysis is later required.

5. Indicative Three-Week Plan (ITDS Pilot)

| Week | Focus | Outcome |
| --- | --- | --- |
| 1 | ITDS ingestion + validation layer; request all dependencies; agree thresholds | Normalised ITDS dataset (actual vs forecast) with full cell-level audit trail. |
| 2 | Variance engine + configurable materiality flagging; begin Teams / KB integration if access granted | Reproducible variance output for ITDS with flagged material lines. |
| 3 | Draft commentary via LLM; connect Aurilo LLM; end-to-end demo | Working demo: material variances detected and draft executive commentary generated for Finance review. |

Note: the timeline assumes the blocking dependencies in Section 4.1 are provided early in Week 1. Delay in any of them — most commonly LLM access and Teams bot approval — will move the corresponding pilot capability into a later phase.

6. Requested Next Steps

Confirm:  the ITDS Minimum Viable Pilot scope described above.

Provision:  provision the three blocking dependencies (Section 4.1) in Week 1.

Confirm:  the Previous Forecast column reading (Section 4.2, ~80% confidence) and name the Finance reviewer.

Agree:  the remaining brief requirements (MS, Group, validation gate, governance) as a Phase 2.

This document is a scope and dependency response intended to align expectations before the pilot begins. Final implementation will confirm data sources, permissions, approval rules and integration architecture, as noted in the brief.